# 5. Gantt Chart & PERT/CPM Network

# 1. Work Breakdown Structure (WBS)

| Code | Activity | Duration (Weeks) |
| --- | --- | --- |
| A | Requirement Analysis | 2 |
| B | System Architecture Design | 2 |
| C | Sensor Data & Dataset Preparation | 2 |
| D | UI/UX Design (Figma) | 2 |
| E | Fire & Gas Detection Module | 4 |
| F | ML Fault Detection Module | 3 |
| G | Dashboard & Alerts Development | 3 |
| H | Integration & System Testing | 3 |
| I | Performance & Safety Testing | 2 |
| J | Deployment | 1 |
| K | Documentation & Closure | 1 |

# 2. Network Dependencies

Project flow:

A → B

After B, parallel work starts:

Path 1:

B → C → E

Path 2:

B → D → F

Both merge at:

E & F → G

Then:

G → H → I → J → K

# 3. PERT Analysis

### 🔹 Activity E – Fire & Gas Detection

- O = 3

- M = 4

- P = 6

TE = (O + 4M + P) / 6
TE = (3 + 16 + 6) / 6 = 4 weeks

### 🔹 Activity F – ML Fault Detection

- O = 2

- M = 3

- P = 5

TE = (2 + 12 + 5) / 6 = 3 weeks

### 🔹 Activity H – Integration Testing

- O = 2

- M = 3

- P = 4

TE = (2 + 12 + 4) / 6 = 3 weeks

# 4. CPM Calculation (Forward Pass)

| Activity | ES | EF |
| --- | --- | --- |
| A (2) | 0 | 2 |
| B (2) | 2 | 4 |
| C (2) | 4 | 6 |
| D (2) | 4 | 6 |
| E (4) | 6 | 10 |
| F (3) | 6 | 9 |
| G (3) | 10 | 13 |
| H (3) | 13 | 16 |
| I (2) | 16 | 18 |
| J (1) | 18 | 19 |
| K (1) | 19 | 20 |

👉 Total Duration = 20 Weeks

# 5. Backward Pass

| Activity | LF | LS |
| --- | --- | --- |
| K | 20 | 19 |
| J | 19 | 18 |
| I | 18 | 16 |
| H | 16 | 13 |
| G | 13 | 10 |
| E | 10 | 6 |
| F | 10 | 7 |
| C | 6 | 4 |
| D | 7 | 5 |
| B | 4 | 2 |
| A | 2 | 0 |

# 6. Slack Calculation

| Activity | Slack |
| --- | --- |
| A | 0 |
| B | 0 |
| C | 0 |
| D | 1 |
| E | 0 |
| F | 1 |
| G | 0 |
| H | 0 |
| I | 0 |
| J | 0 |
| K | 0 |

# Critical Path

A → B → C → E → G → H → I → J → K

👉 Total Duration = 20 Weeks

# 7. Gantt Chart Explanation

- Tasks A and B are sequential

- After B:

  - C & D run in parallel

- E depends on C

- F depends on D

- G depends on E & F

- Remaining tasks are sequential

👉 Critical path tasks are highlighted
👉 Parallel tasks:

- C & D

- E & F

# FINAL SUMMARY

| Metric | Value |
| --- | --- |
| Total Duration | 20 Weeks |
| Critical Path | A-B-C-E-G-H-I-J-K |
| Parallel Tasks | C & D, E & F |
| Slack | D & F (1 Week) |

# Conclusion

The project focuses primarily on fire and gas detection using sensor data, with an additional machine learning module for fault detection. The critical path shows that sensor data processing and detection modules are the most time-sensitive tasks. The project is estimated to be completed in 20 weeks with efficient parallel execution of UI and ML components.

Gantt Chart