# Assignment 8 – Sprint Planning and Velocity Calculation

# 1. Introduction

This assignment focuses on Sprint Planning and Velocity Calculation using Agile Scrum methodology for the Fire and Gas Detection System with ML-based Fault Detection.

The project was managed using Jira Software, where user stories were organized into sprints and tracked using Scrum boards.

Sprint planning helped define achievable goals, while velocity calculation helped measure team performance and improve future sprint estimation.

# 2. Sprint 1 Planning

## 2.1 Planning Strategy

During Sprint 1, the team focused on implementing core system functionalities required for basic system operation:

- User Authentication (Login System)

- Dashboard Visualization

- Log Monitoring System

- Basic Alert System

- Log Filtering Functionality

These features are essential for enabling real-time monitoring and system interaction.

## 2.2 Sprint Goal

To implement core monitoring features including login, dashboard, logs, and alert system for the Fire and Gas Detection System.

## 2.3 Sprint Duration

Sprint 1 Duration: 2 Weeks
(Example: 1 March – 14 March)

## 2.4 Sprint 1 Backlog

| Task | Story Points | Status |
| --- | --- | --- |
| Login to System | 2 | Done |
| View Dashboard | 3 | Done |
| View Logs | 3 | Done |
| Filter Logs | 2 | In Progress |
| View Alerts | 3 | In Progress |
| Run ML Prediction | 5 | To Do |
| View Reports | 3 | To Do |

Total Planned Work = 21 Story Points

## 2.5 Planned Velocity

Initially estimated based on team capacity:

Planned Velocity = 20 Story Points per Sprint

# 3. Sprint 1 Execution and Velocity

## 3.1 Actual Progress

At the end of Sprint 1:

- Completed Work = 8 Story Points

- In Progress Work = 5 Story Points

- Not Started Work = 8 Story Points

Only completed work is counted in velocity.

## 3.2 Actual Velocity Calculation

Velocity = Total Story Points Completed

Actual Velocity = 8 Story Points

## 3.3 Analysis of Sprint 1

The sprint was not fully completed as planned. The team committed to 21 story points but completed only 8 story points.

Reasons include:

- Underestimation of ML prediction complexity

- Additional time required for dashboard UI integration

- Log filtering logic required more testing

- Time spent debugging real-time data flow

This showed that the initial estimation was optimistic.

# 4. Sprint 2 Planning

## 4.1 Planning Strategy

Sprint 2 planning was based on the actual velocity from Sprint 1 (8 story points), instead of the planned velocity.

This ensures realistic sprint commitments.

## 4.2 Sprint Goal

To complete ML fault detection and reporting features while improving alert system reliability.

## 4.3 Sprint Duration

Sprint 2 Duration: 15 March – 28 March (2 Weeks)

## 4.4 Available Backlog Stories

| Task | Story Points |
| --- | --- |
| Run ML Prediction | 5 |
| View Reports | 3 |
| Improve Alerts System | 3 |
| Advanced Log Filtering | 2 |
| Performance Optimization | 5 |

Total Available Work = 18 Story Points

## 4.5 Sprint Planning Decision

Since Actual Velocity = 8 Story Points, the team selected:

| Selected Task | Story Points |
| --- | --- |
| Run ML Prediction | 5 |
| View Reports | 3 |

Total Selected Work = 8 Story Points

This keeps the sprint goal achievable and aligned with team performance.

## 4.6 Remaining Work (Future Sprints)

- Improve Alerts System (3)

- Advanced Log Filtering (2)

- Performance Optimization (5)

These will be planned in future sprints.

# 5. Velocity Comparison Table

| Sprint | Planned Points | Completed Points | Velocity |
| --- | --- | --- | --- |
| Sprint 1 | 21 | 8 | 8 |
| Sprint 2 | 8 (Adjusted) | — | — |

# 6. Key Observations

- Sprint 1 revealed the actual team working capacity

- Initial estimation was optimistic

- Velocity calculation provided measurable performance data

- Sprint 2 planning became realistic and data-driven

- Agile supports continuous improvement

# 7. Conclusion

Sprint Planning and Velocity Calculation are important components of Agile project management.

In this project, the team initially planned 21 story points but completed only 8, highlighting estimation challenges.

By using actual velocity as the basis for Sprint 2 planning, the team adopted a more realistic and sustainable approach. This demonstrates how Agile methodology supports adaptive planning, continuous improvement, and better project execution.