4. Perform FP Analysis and use COCOMO for Software Estimation

# FUNCTION POINT (FP) ANALYSIS

## Step 1: Identify Functional Components

### 1. External Inputs (EI)

Inputs provided by users or system

| Input | Count |
| --- | --- |
| User Login | 1 |
| Sensor Data Input (Gas) | 1 |
| Sensor Data Input (Temperature) | 1 |
| Log Data Generation | 1 |
| Threshold Configuration | 1 |
| Filter Logs Input | 1 |
| ML Model Input (Logs) | 1 |

Total EI = 7
Weight (Average) = 4

👉 EI FP = 7 × 4 = 28

### 2. External Outputs (EO)

System-generated outputs

| Output | Count |
| --- | --- |
| Dashboard Display | 1 |
| Gas Level Display | 1 |
| Temperature Display | 1 |
| Alert Notifications | 1 |
| ML Prediction Result | 1 |
| Reports Generation | 1 |

Total EO = 6
Weight = 5

👉 EO FP = 6 × 5 = 30

### 3. External Inquiries (EQ)

Simple queries

| Inquiry | Count |
| --- | --- |
| View Logs | 1 |
| Filter Logs | 1 |
| View Reports | 1 |

Total EQ = 3
Weight = 4

👉 EQ FP = 3 × 4 = 12

### 4. Internal Logical Files (ILF)

Internal data storage

| File | Count |
| --- | --- |
| Sensor Data Database | 1 |
| Logs Database | 1 |
| Alerts Database | 1 |
| User Data | 1 |
| ML Model Data | 1 |

Total ILF = 5
Weight = 10

👉 ILF FP = 5 × 10 = 50

### 5. External Interface Files (EIF)

External systems

| External System | Count |
| --- | --- |
| ESP32 Device | 1 |
| Notification System | 1 |
| Cloud Storage | 1 |

Total EIF = 3
Weight = 7

👉 EIF FP = 3 × 7 = 21

## Step 2: Unadjusted Function Points (UFP)

| Component | FP |
| --- | --- |
| EI | 28 |
| EO | 30 |
| EQ | 12 |
| ILF | 50 |
| EIF | 21 |

👉 Total UFP = 141

## Step 3: Value Adjustment Factor (VAF)

System Characteristics:

- Real-time monitoring

- IoT-based system

- ML-based fault detection

- High reliability requirement

- Real-time alerts

- Data processing system

Assume:
DI = 14 × 3 = 42

VAF Formula:

VAF = 0.65 + (0.01 × DI)

VAF = 0.65 + 0.42 = 1.07

## Step 4: Final Function Points

FP = UFP × VAF

FP = 141 × 1.07

FP ≈ 151 Function Points

# BASIC COCOMO MODEL

## Step 1: Convert FP to LOC

Assume:
1 FP ≈ 50 LOC

LOC = 151 × 50

LOC ≈ 7,550

KLOC = 7.55

## Step 2: Select COCOMO Mode

Project Type:

- IoT-based system

- Real-time monitoring

- Moderate complexity

👉 Semi-Detached Mode

Constants:

- a = 3.0

- b = 1.12

- c = 2.5

- d = 0.35

## Step 3: Effort Estimation

Effort = a × (KLOC)^b

Effort = 3.0 × (7.55)^1.12

(7.55)^1.12 ≈ 8.7

Effort ≈ 3.0 × 8.7

Effort ≈ 26.1 Person-Months

## Step 4: Development Time

Time = c × (Effort)^d

Time = 2.5 × (26.1)^0.35

(26.1)^0.35 ≈ 3.0

Time ≈ 2.5 × 3.0

Time ≈ 7.5 months

## Step 5: Team Size

Team Size = Effort / Time

Team Size = 26.1 / 7.5

Team Size ≈ 3–4 members